Governance and Management structure of the PPP

*Accelerating local Action in Humanitarian Aid and Health* Crises

**Governance Structure (guidance and decision making)**

|  |  |  |
| --- | --- | --- |
|  | External | Internal |
| Global | **Global External Steering Group**  Annual meeting:  ECHO DDG  ECHO HoU D/1  Dir DCC and PRD  3 EUNSs  2 HNS  RCEU Office Director  ECHO (tbc) | **Global Internal Steering Group**    USGs GRHDD and NSDOC  Dir DCC and PRD  3 EUNSs (rotational basis)  2 Deputy Regional Directors (rotational basis)  2 HNS (rotational basis)  RCEU Office Director   * Quarterly meeting aiming to reach decision by consensus. * If no decision reached escalate to the IFRC SG. * Supported by the grant management team based in IFRC PRD. |
| + integrate into the High-Level Dialogue DG ECHO – IFRC network meeting |

**At Country level**

|  |  |  |
| --- | --- | --- |
|  | External | Internal |
| Country Coordination Group  *NB: this structure a mix of governance and management* | **Country Advisory Group**  HNS  Lead EUNS – convener  IFRC Rep/HoD  ECHO TA  Decide at country level frequency of meeting with a minimum of biannual and where feasible and relevant invite government representative. | **Country Operational Coordination Group**  HNS – co-facilitator  Lead EUNS – co-facilitator  IFRC Rep/HoD  EUNss involved in the programme  Decide at country level frequency of meeting with a minimum of quarterly meetings. |

**Management Structure (coordinate and manage implementation)**

|  |  |
| --- | --- |
|  | Internal |
| Global | **Grant Management Team**  Full-time grant coordinator (in PRD); and dedicated part-time capacity in PMER/data analysis, Finance, admin support  Ensures global compliance with the PPP grant requirements  Follow the implementation of the PPP and ensure timely reporting  Provide support to the organization of the global steering groups (internal and external) : agendas, supporting documents, etc.  The implementation of the PPP will also be supported by the 5 Thematic groups that will continue to provide analysis and technical support on substantive areas (may add some EUNS members and others technical topics as relevant)  Global component working group continues to provide analysis and technical support on cross-cutting areas  **The role of both the Grant Management Team and the 5 thematic groups will be to ensure Global coherence.** |
| Regional | **Regional Operational Coordination Forum**  Regional grant coordinator (to be appointed by each Region)  Deputy Regional director  Regional PRD, PMER, Finance, HDCC  Lead EU NSs  HNS at senior management level (heads of relevant departments)  IFRC country representative/HoD  Meet regularly at a minimum at quarterly basis to ensure consistent guidance, exchange of best practices and learning, address challenges and ensure overall accountability |